## 00_Index
Northstar Systems — Operational AI Copilot Demo Data
Synthetic company, customers, suppliers and records for the Operational AI Copilot prototype. All content is fictional.
# | Domain | File / Sheet | Format | Example question the Copilot should answer
1 | Product | product_roadmap_q3 | Markdown | 产品路线图的主要目标与未决事项是什么？ / What are the roadmap's main Q3 goals and open items?
2 | Customer Experience | customer_feedback_q3 | CSV | 哪些客户痛点重复出现？ / Which customer pain points recur most frequently?
3 | Customer Support | support_incidents | Markdown | 哪些问题需要优先升级？ / Which incidents need priority escalation?
4 | Market | market_research_europe | Markdown | 哪些市场需求有资料支持？ / Which market needs are backed by evidence?
5 | Commercial / Sales | sales_pipeline | CSV | 哪些商机需要补充信息或优先跟进？ / Which opportunities need follow-up or are at risk?
6 | Quotation | commercial_quote_001 | Markdown | 报价有哪些成本假设和风险？ / What cost assumptions and risks sit behind this quote?
7 | Customer Requirements | customer_requirements_001 | Markdown | 客户要求与当前产品能力有哪些差距？ / What gaps exist between customer requirements and current capability?
8 | Supply Chain | supplier_status | CSV | 哪些交付事项可能影响客户承诺？ / Which supplier issues could affect customer commitments?
9 | NPI | npi_readiness | Markdown | 新产品导入还有哪些未关闭事项？ / What NPI items are still open?
10 | Operations | weekly_operations_review | Markdown | 哪些问题影响成本、质量或交付？ / What's affecting cost, quality or delivery this week?
11 | Program / Project | project_action_log | CSV | 哪些行动逾期、存在依赖或尚未确认负责人？ / Which actions are overdue, blocked, or unowned?
12 | Decisions | decision_log | Markdown | 哪些决定已批准，哪些仍在等待确认？ / Which decisions are approved vs pending?
Entity notes: Company = Northstar Systems Ltd (fictional B2B industrial IoT vendor, product: NorthGuard IIoT Platform). Customers: Meridian Steel Group, Atlas Foundry Co., Bannerman Logistics, Kestrel Energy Systems, Dorsett Manufacturing, Caldwell Precision Components, Vantage Rail Systems, Harrow Industrial Holdings. Suppliers: Ferrotech Sensors Ltd, Helion Electronics GmbH, Baltic Components SA, CloudEdge Compute Ltd, Nordic Cabling AB. Team: Ji Xiong (Ops lead), Elena Marsh (Product), Tom Okafor (Engineering), Priya Nandan (Customer Success), Felix Grant (Supply Chain), Sara Lindqvist (Sales), Daniel Price (Finance). 'Today' for this dataset is 2026-10-15; most recent weekly ops review covers 2026-10-05 to 2026-10-11.

## 01_customer_feedback_q3
feedback_id | date | customer | channel | theme | detail | severity | status
FB-001 | 2026-07-08 | Meridian Steel Group | Support ticket | False positive alerts | Vibration alert triggered on Line 3 gearbox with no fault found on inspection; third occurrence this month. | High | Closed - fed into Alerts 2.0 fix
FB-002 | 2026-07-15 | Bannerman Logistics | QBR call | Dashboard load time | Asset Health Dashboard takes 12-15s to load for sites with 40+ assets; used daily by shift supervisors. | Medium | Open
FB-003 | 2026-07-22 | Dorsett Manufacturing | Support ticket | Missing export feature | No way to export asset health report to Excel for weekly maintenance meeting; currently screenshotting. | Medium | Open
FB-004 | 2026-07-29 | Atlas Foundry Co. | Email | Onboarding complexity | Sensor commissioning wizard unclear on calibration step; site engineer needed 2 support calls to complete. | Medium | Closed - help article updated
FB-005 | 2026-08-03 | Kestrel Energy Systems | QBR call | Energy add-on interest | Strong interest in Energy Optimization add-on; asked for pricing and whether it covers 3-phase motor loads. | Low | Closed - routed to Sales, see sales_pipeline.csv OPP-2044
FB-006 | 2026-08-05 | Harrow Industrial Holdings | Support ticket | False positive alerts | Repeated bearing-wear alerts on Site 2 conveyor motors not matched by maintenance findings. | High | Closed - fed into Alerts 2.0 fix
FB-007 | 2026-08-11 | Meridian Steel Group | Support ticket | Multi-site visibility | No single view across Sheffield and Scunthorpe sites; ops manager must log in twice. | High | Open - linked to Fleet Rollup, see product_roadmap_q3.md
FB-008 | 2026-08-14 | Caldwell Precision Components | Email | Onboarding delay | Sensor install delayed 3 weeks waiting on gateway hardware shipment. | Medium | Open - see supplier_status.csv HEL-004
FB-009 | 2026-08-19 | Vantage Rail Systems | Support ticket | Missing export feature | Compliance team needs exportable asset condition reports for internal audit; currently unsupported. | High | Open
FB-010 | 2026-08-25 | Harrow Industrial Holdings | QBR call | Multi-site visibility | Requested a rollup view across 5 sites ahead of board review; cited as a renewal consideration. | High | Open - linked to Fleet Rollup
FB-011 | 2026-09-02 | Dorsett Manufacturing | Support ticket | Alert fatigue | Maintenance team muting alerts on 2 assets due to volume of low-confidence notifications. | High | Closed - fed into Alerts 2.0 fix
FB-012 | 2026-09-09 | Bannerman Logistics | Support ticket | Mobile app | Warehouse technicians want offline access to asset status when moving between low-signal areas. | Medium | Open - linked to mobile offline mode, deprioritised to Q4
FB-013 | 2026-09-14 | Atlas Foundry Co. | Email | Pricing query | Asked whether Energy Optimization add-on pricing is per-site or per-asset ahead of budget planning. | Low | Open - pricing not finalised, see commercial_quote_001.md
FB-014 | 2026-09-20 | Meridian Steel Group | Support ticket | False positive alerts | Post Alerts 2.0 release, false-positive rate improved but still 2-3 per week on Line 3; below expectation set by Northstar. | Medium | Open
FB-015 | 2026-09-24 | Kestrel Energy Systems | Support ticket | Energy add-on data gap | Energy Optimization beta dashboard shows a gap in data for 2026-09-18 to 2026-09-19; suspected gateway outage. | Medium | Open
FB-016 | 2026-09-29 | Vantage Rail Systems | QBR call | Missing export feature | Reiterated export requirement; flagged as a condition for expanding to 2 additional depots in 2027. | High | Open - linked to sales_pipeline.csv OPP-2058

## 02_sales_pipeline
opportunity_id | customer | region | stage | value_gbp | probability_pct | next_step | owner | target_close_date | notes_gaps
OPP-2019 | Meridian Steel Group | UK | Negotiation | 142000 | 70 | Finalise Fleet Rollup commitment language in contract addendum | Sara Lindqvist | 2026-11-15 | Customer wants written commitment on Fleet Rollup date before signing expansion; roadmap currently shows Q4, not yet date-certain (see product_roadmap_q3.md).
OPP-2031 | Harrow Industrial Holdings | UK | Negotiation | 98000 | 65 | Confirm Fleet Rollup scope for 5-site view | Sara Lindqvist | 2026-11-30 | Renewal at risk if multi-site visibility (FB-010) not resolved; board review scheduled late Nov.
OPP-2044 | Kestrel Energy Systems | Nordics | Proposal sent | 61000 | 55 | Await Energy Optimization add-on final pricing | Sara Lindqvist | 2026-12-10 | Pricing gap: proposal sent with placeholder pricing, see commercial_quote_001.md note; FB-005 and FB-015 both from this account.
OPP-2051 | Atlas Foundry Co. | Germany | Qualification | 45000 | 30 | Clarify Energy Optimization pricing model (per-site vs per-asset) | Sara Lindqvist | 2027-01-20 | Customer paused discussion pending pricing answer (FB-013).
OPP-2058 | Vantage Rail Systems | Germany | Proposal sent | 210000 | 40 | Confirm export/reporting feature commitment for compliance use case | Sara Lindqvist | 2027-02-15 | Largest open deal; expansion to 2 additional depots explicitly conditional on export feature (FB-016); feature not yet scheduled.
OPP-2063 | Caldwell Precision Components | Poland | Negotiation | 38000 | 60 | Resolve gateway delivery delay before expansion sign-off | Sara Lindqvist | 2026-11-20 | Customer cautious about expanding while existing onboarding (INC-114) is still blocked on hardware.
OPP-2070 | Bannerman Logistics | UK | Qualification | 27000 | 25 | Scope offline mobile mode requirement with Engineering | Sara Lindqvist | 2027-01-10 | Expansion to second warehouse contingent on offline mode per customer, which is deprioritised to Q4/Q1 (see product_roadmap_q3.md).
OPP-2075 | Dorsett Manufacturing | UK | Prospecting | 15000 | 15 | Introduce export feature roadmap once scheduled | Sara Lindqvist | 2027-03-01 | Early-stage upsell conversation; export gap (FB-003) raised informally.

## 03_supplier_status
supplier_id | supplier | component | lead_time_weeks_normal | lead_time_weeks_current | status | risk_level | delivery_commit_date | notes
FER-001 | Ferrotech Sensors Ltd | Vibration sensor (NorthGuard VS-200) | 3 | 3 | On track | Low | 2026-10-20 | No change from normal lead time; consistent performer across Q3.
HEL-004 | Helion Electronics GmbH | Edge Gateway v1 (NorthGuard EG-100) | 4 | 7 | Delayed | High | 2026-09-26 | Component shortage on gateway main board; directly causing INC-114 (Caldwell Precision Components) and risk to Harrow Industrial Holdings quote QUOTE-2026-041. Escalated by Felix Grant 2026-09-05, no confirmed recovery date.
BAL-002 | Baltic Components SA | PCB assemblies & connectors | 2 | 2 | On track | Low | 2026-10-12 | Stable; used in both VS-200 sensor and EG-100 gateway builds.
CLE-003 | CloudEdge Compute Ltd | Edge compute unit (for Energy Optimization add-on) | 5 | 6 | Minor delay | Medium | 2026-11-03 | Slight slip due to shared production line with a non-Northstar customer order; monitor for further slippage ahead of Energy Optimization Q4 rollout.
NOR-005 | Nordic Cabling AB | Industrial sensor cabling | 2 | 2 | On track | Low | 2026-10-15 | No issues; regional supplier for Nordics installs (Kestrel Energy Systems).
HEL-006 | Helion Electronics GmbH | Edge Gateway v2 (NorthGuard EG-200, in development) | 6 | Not yet in production | Pre-production | Medium | TBC | Planned for NorthGuard Edge Gateway v2 NPI (see npi_readiness.md); given HEL-004 delay on v1 gateway, lead-time risk for v2 has not been independently reassessed.

## 04_project_action_log
action_id | description | owner | due_date | status | dependency | priority
ACT-201 | Recalibrate Line 3 gearbox alert threshold (interim fix) | Tom Okafor | 2026-07-19 | Closed | None | High
ACT-205 | Update sensor commissioning help article and in-app copy | Priya Nandan | 2026-08-01 | Closed | None | Medium
ACT-212 | Escalate EG-100 gateway delay to Helion Electronics GmbH account manager | Felix Grant | 2026-09-05 | Closed - escalated, outcome pending | Supplier response | High
ACT-218 | Engineering estimate for Fleet Rollup dashboard | Tom Okafor | 2026-09-25 | Overdue | None | High
ACT-221 | Finalise Energy Optimization add-on pricing model | Daniel Price | 2026-09-30 | Overdue | Input from Elena Marsh on feature scope | High
ACT-224 | Scope offline mobile mode for Bannerman Logistics / general roadmap | Elena Marsh | 2026-10-15 | Open | None | Low
ACT-227 | Obtain Finance Director sign-off on QUOTE-2026-041 discount (8%) | Daniel Price | 2026-10-05 | Overdue | None | Medium
ACT-230 | Investigate INC-122 missing energy data (Kestrel Energy Systems) | Unassigned | 2026-10-09 | Overdue - no owner assigned | Gateway diagnostic log access | High
ACT-233 | Shortlist backup PCB/board supplier for EG-200 to reduce single-source risk | Felix Grant | 2026-10-23 | Open | None | High
ACT-236 | Confirm whether export/reporting feature (REQ-03) can be scheduled for Q4 | Elena Marsh | 2026-10-20 | Open | Engineering capacity after Alerts 2.0 follow-up | High
ACT-239 | Reconcile QUOTE-2026-041 Year-1 total vs sales_pipeline.csv OPP-2031 headline value | Daniel Price | 2026-10-16 | Open | None | Medium
ACT-241 | Assess additional storage cost for extending data retention from 18 months to 3 years (Vantage Rail Systems requirement) | Tom Okafor | 2026-10-30 | Open | None | Medium

## 05_product_roadmap_q3
Product Roadmap — Q3 2026 (Jul–Sep)
**Product:** NorthGuard IIoT Platform (Predictive Maintenance & Asset Health)
**Owner:** Elena Marsh, Product Manager
**Status as of:** 2026-10-01
Q3 Goals
1. Ship Predictive Maintenance Alerts 2.0 — reduce false-positive alert rate from 18% to under 8%.
2. Release Energy Optimization add-on (beta) to 3 pilot customers.
3. Cut average customer onboarding time from 6 weeks to 4 weeks.
4. Deliver multi-site "Fleet Rollup" dashboard for customers with 3+ sites.
Delivered in Q3
• Predictive Maintenance Alerts 2.0 shipped 2026-09-12. Early data (4 weeks post-launch,
Meridian Steel Group and Dorsett Manufacturing) shows false-positive rate down to 11%,
short of the 8% target — see customer_feedback_q3.csv (FB-014) for ongoing complaints.
• Energy Optimization add-on beta shipped to 2 of 3 planned pilots (Kestrel Energy Systems,
Harrow Industrial Holdings). Third pilot (Caldwell Precision Components) slipped to
Q4 pending gateway hardware — see npi_readiness.md and supplier_status.csv (Helion
Electronics GmbH delay).
• Onboarding time reduced to 5.1 weeks average (target 4 weeks) — partially achieved.
Slipped to Q4 2026
• Fleet Rollup dashboard: design complete, engineering estimate 5 weeks; not started in Q3
due to Engineering capacity being redirected to Alerts 2.0 false-positive fixes.
Requested by 4 of 8 active customers (see customer_feedback_q3.csv, sales_pipeline.csv
opportunity OPP-2031).
• Native mobile app offline mode: scoped, not started. Lower priority than Fleet Rollup
per Elena Marsh / Tom Okafor review on 2026-09-18 (see decision_log.md DEC-011).
• CSV/Excel export of asset health reports: repeatedly requested (FB-003, FB-009, FB-016);
not yet scheduled — candidate for Q4 "quick win" sprint.
Open Risks for Q4 Planning
• False-positive rate still above target; may need a second iteration of Alerts 2.0 before
Fleet Rollup work starts, which would push Fleet Rollup further into Q4.
• Energy Optimization add-on pricing not finalised — see commercial_quote_001.md note on
Harrow Industrial Holdings quote, which excludes the add-on pending pricing sign-off.
• Hardware dependency on Helion Electronics GmbH (gateway lead time) affects both the
third Energy Optimization pilot and the planned Q4 NorthGuard Edge Gateway v2 rollout
(see npi_readiness.md).

## 06_support_incidents
Support Incident Log — Q3 2026
**Owner:** Priya Nandan, Customer Success Manager
**Status as of:** 2026-10-02
INC-101 ¦ High ¦ Closed
• **Customer:** Meridian Steel Group
• **Date raised:** 2026-07-08
• **Summary:** Repeated false-positive vibration alerts on Line 3 gearbox (3 occurrences in July).
• **Root cause:** Alert threshold model not calibrated for Line 3's variable load profile.
• **Resolution:** Threshold recalibrated 2026-07-19; longer-term fix folded into Alerts 2.0
(shipped 2026-09-12). Linked to customer_feedback_q3.csv FB-001.
• **Closed:** 2026-07-19 (interim); monitored post Alerts 2.0 release, see FB-014 for residual issue.
INC-108 ¦ Medium ¦ Closed
• **Customer:** Atlas Foundry Co.
• **Date raised:** 2026-07-24
• **Summary:** Sensor commissioning failed twice during onboarding; calibration step unclear.
• **Root cause:** Commissioning wizard copy did not match updated sensor firmware UI.
• **Resolution:** Help article and in-app copy corrected 2026-08-01.
• **Closed:** 2026-08-01.
INC-114 ¦ High ¦ Open — needs escalation
• **Customer:** Caldwell Precision Components
• **Date raised:** 2026-08-14
• **Summary:** Onboarding blocked; edge gateway hardware not yet delivered (ordered 2026-07-20,
original ETA 2026-08-10, now slipped to 2026-09-26 per supplier).
• **Root cause:** Supplier-side component shortage at Helion Electronics GmbH (see
supplier_status.csv, HEL-004).
• **Impact:** Delays third Energy Optimization pilot (see product_roadmap_q3.md); customer go-live
now 6 weeks late against contracted onboarding SLA (4 weeks).
• **Status:** Open. Felix Grant (Supply Chain) escalated to Helion account manager 2026-09-05;
no confirmed ship date as of 2026-10-02. **Recommend escalation to Felix Grant and Elena Marsh
this week — SLA breach risk.**
INC-119 ¦ High ¦ Closed
• **Customer:** Harrow Industrial Holdings
• **Date raised:** 2026-08-05
• **Summary:** Repeated bearing-wear alerts on Site 2 conveyor motors not confirmed by physical inspection.
• **Root cause:** Same alert-model limitation as INC-101, different asset class (conveyor vs gearbox).
• **Resolution:** Included in Alerts 2.0 scope; confirmed improved post-release by customer on QBR call 2026-09-20.
• **Closed:** 2026-09-12.
INC-122 ¦ Medium ¦ Open
• **Customer:** Kestrel Energy Systems
• **Date raised:** 2026-09-24
• **Summary:** Energy Optimization beta dashboard shows missing data 2026-09-18 to 2026-09-19.
• **Root cause (suspected, unconfirmed):** Gateway connectivity outage at customer site; not yet
verified against gateway logs.
• **Status:** Open. Engineering (Tom Okafor) to pull gateway diagnostic logs — **no owner
confirmed as of 2026-10-02; action not yet logged in project_action_log.csv.**
INC-126 ¦ Low ¦ Open
• **Customer:** Bannerman Logistics
• **Date raised:** 2026-09-09
• **Summary:** Request (not a defect) for offline mobile access in low-signal warehouse zones.
• **Status:** Logged as product feedback, not a support defect. See customer_feedback_q3.csv FB-012
and product_roadmap_q3.md (mobile offline mode deprioritised to Q4).
Summary (Q3)
• 6 incidents logged; 4 closed, 2 open.
• 2 of 4 closed incidents (INC-101, INC-119) were different manifestations of the same
root cause (alert-model calibration), now addressed by Alerts 2.0 — though FB-014 suggests
the fix is incomplete.
• 1 open incident (INC-114) carries SLA breach risk and is supplier-dependent.
• 1 open incident (INC-122) currently has no assigned owner.

## 07_market_research_europe
Market Research — European Industrial IoT / Predictive Maintenance
**Prepared by:** Sara Lindqvist, Sales Director (Nordics), with input from Elena Marsh
**Status as of:** 2026-09-15
**Note:** Competitor names below are illustrative placeholders used for internal positioning
discussion, not confirmed market-share figures from a named research firm.
Demand Signals
• UK: Continued push from manufacturers to cut unplanned downtime amid energy cost pressure;
steel and foundry accounts (our current base) show the strongest willingness to pay for
predictive maintenance over basic condition monitoring.
• Germany: Larger, more technically sophisticated buyers (e.g. rail and precision component
segments); longer sales cycles, stronger expectation of on-prem/edge data processing and
detailed audit/export capability — consistent with Vantage Rail Systems' requirements
(see customer_requirements_001.md).
• Poland: Growing interest from mid-size component manufacturers seeking lower-cost entry
points; price sensitivity higher than UK/Germany; hardware lead times are a bigger
competitive factor here because budget cycles are tighter.
• Nordics: Strong fit with energy-cost-driven buyers (utilities, energy-intensive
manufacturing); Energy Optimization add-on resonates well in early conversations
(see sales_pipeline.csv OPP-2044, Kestrel Energy Systems).
Regulatory Context (directional, not legal advice)
• EU Machinery Regulation and increasing corporate energy-reporting expectations are
pushing industrial customers toward systems that can produce auditable condition and
energy-usage records — relevant to the repeated export/reporting requests in
customer_feedback_q3.csv (FB-003, FB-009, FB-016) and customer_requirements_001.md.
• Treat this as a product-prioritisation signal, not a compliance determination; Northstar
does not currently claim formal regulatory certification for its reporting outputs.
Illustrative Competitive Landscape
¦ Competitor (placeholder name) ¦ Positioning ¦ Perceived strength ¦ Perceived gap ¦
¦---¦---¦---¦---¦
¦ PredictAxis ¦ Enterprise-focused, heavy ML ¦ Strong brand with large OEMs ¦ Slower onboarding, high price point ¦
¦ SentinelWorks ¦ Mid-market condition monitoring ¦ Lower cost, fast install ¦ Limited predictive accuracy, basic dashboards ¦
¦ FactoryPulse ¦ Energy-monitoring specialist ¦ Strong energy reporting ¦ Weak predictive-maintenance depth ¦
Northstar's current differentiation: combined predictive maintenance + emerging energy
optimization in one platform, with mid-market pricing — closest in positioning to
FactoryPulse on energy, and SentinelWorks on price, but ahead of both on breadth.
Implications for Roadmap / Commercial
• Export/reporting features (currently a recurring gap — see product_roadmap_q3.md) are
becoming a market-entry requirement in Germany and a renewal factor in the UK, not just
a "nice to have."
• Energy Optimization add-on pricing should be finalised ahead of Q4; multiple live
opportunities (OPP-2044, OPP-2051) are waiting on it (see sales_pipeline.csv).
• Poland pipeline will be more sensitive to supplier lead-time issues (see supplier_status.csv)
than UK/Germany pipeline, given tighter customer budget cycles.

## 08_commercial_quote_001
Commercial Quote — QUOTE-2026-041
**Customer:** Harrow Industrial Holdings
**Prepared by:** Daniel Price, Finance Analyst / Sara Lindqvist, Sales Director
**Date:** 2026-09-28
**Linked opportunity:** sales_pipeline.csv OPP-2031
Scope
Expansion of existing NorthGuard IIoT Platform deployment from 2 sites to 5 sites
(Site 3, 4, 5), including hardware, software subscription, and installation services.
Fleet Rollup dashboard access included once generally available (see product_roadmap_q3.md;
not yet shipped as of quote date).
Line Items
¦ Item ¦ Qty ¦ Unit price (GBP) ¦ Line total (GBP) ¦
¦---¦---¦---¦---¦
¦ NorthGuard Vibration Sensor (per asset) ¦ 60 ¦ 180 ¦ 10,800 ¦
¦ NorthGuard Edge Gateway v1 (per site) ¦ 3 ¦ 1,450 ¦ 4,350 ¦
¦ Installation & commissioning (per site) ¦ 3 ¦ 2,200 ¦ 6,600 ¦
¦ Software subscription — Predictive Maintenance (per asset / year) ¦ 60 ¦ 420 ¦ 25,200 ¦
¦ Software subscription — Asset Health Dashboard (per site / year) ¦ 3 ¦ 1,800 ¦ 5,400 ¦
¦ Onboarding & training (one-off) ¦ 1 ¦ 3,500 ¦ 3,500 ¦
¦ **Subtotal** ¦ ¦ ¦ **55,850** ¦
¦ Volume discount (8%, 5+ site commitment) ¦ ¦ ¦ -4,468 ¦
¦ **Total Year 1 (GBP, ex VAT)** ¦ ¦ ¦ **51,382** ¦
Note: total above covers Year 1 only; figure differs from the headline £98,000 shown in
sales_pipeline.csv OPP-2031, which includes a proposed 2-year subscription commitment
(Year 1 + Year 2 renewal) under discussion — **2-year figure not yet confirmed with customer
and should be reconciled before contract issue.**
Cost Assumptions
• Sensor and gateway hardware costed at current Helion Electronics GmbH / Ferrotech Sensors
Ltd supplier pricing as of 2026-09-01 (see supplier_status.csv); not hedged against FX or
component cost movement beyond 2026-12-31.
• Installation cost assumes standard site access; does not include scaffolding, permits, or
out-of-hours work, which affected Site 2 at this customer in the original deployment.
• Energy Optimization add-on is **excluded** from this quote pending finalised pricing
(see market_research_europe.md and customer_feedback_q3.csv FB-013); to be issued as a
separate change order once pricing is approved.
Risks / Open Items
1. Fleet Rollup dashboard is referenced as included but is not yet shipped (slipped to Q4,
see product_roadmap_q3.md) — commercial team should avoid implying a firm delivery date
in customer-facing communication until Engineering confirms one.
2. Gateway hardware lead time currently uncertain due to Helion Electronics GmbH delay
affecting a separate account (Caldwell Precision Components, see supplier_status.csv
HEL-004); if the same delay applies here, the 3-site installation timeline may slip.
3. Discount level (8%) requires Finance Director sign-off above £50,000 total value per
Northstar's standard approval threshold — **sign-off not yet recorded as of 2026-10-02.**

## 09_customer_requirements_001
Customer Requirements — Vantage Rail Systems
**Prepared by:** Elena Marsh, Product Manager (from discovery calls with customer engineering
and compliance teams)
**Date:** 2026-09-10
**Linked opportunity:** sales_pipeline.csv OPP-2058
Background
Vantage Rail Systems (Germany) operates rail maintenance depots and is evaluating NorthGuard
for predictive maintenance on bogie and traction-motor assets across its primary depot, with
an option to expand to 2 further depots in 2027 if initial deployment is successful.
Functional Requirements
¦ ID ¦ Requirement ¦ Priority ¦ Current platform status ¦
¦---¦---¦---¦---¦
¦ REQ-01 ¦ Vibration and temperature monitoring on bogie assemblies ¦ Must have ¦ Supported ¦
¦ REQ-02 ¦ Predictive alerts for traction motor bearing wear ¦ Must have ¦ Supported (Alerts 2.0) ¦
¦ REQ-03 ¦ Exportable condition reports (PDF/Excel) for internal compliance audit ¦ Must have ¦ **Not supported** — see customer_feedback_q3.csv FB-009, FB-016 ¦
¦ REQ-04 ¦ Role-based access control for depot vs HQ compliance users ¦ Must have ¦ Supported ¦
¦ REQ-05 ¦ On-prem or edge-local data processing option (data residency preference) ¦ Should have ¦ Partially supported — edge gateway processes locally, cloud dashboard required for reporting ¦
¦ REQ-06 ¦ Multi-depot rollup view ahead of 2027 expansion ¦ Should have ¦ **Not supported** — linked to Fleet Rollup, see product_roadmap_q3.md ¦
¦ REQ-07 ¦ API access for integration with customer's internal maintenance system (SAP PM) ¦ Could have ¦ Not yet scoped ¦
Non-Functional Requirements
• Dashboard availability target: 99.5% during depot operating hours (06:00–22:00 CET).
• Alert latency: under 5 minutes from anomaly detection to notification (currently meets this).
• Data retention: minimum 3 years for compliance audit purposes (currently 18 months —
**gap, not yet raised with Engineering**).
Gap Summary
Of 7 requirements captured, 2 "must have" items (REQ-03) and one "should have" (REQ-06) are
not currently supported. REQ-03 (export) is the most commercially urgent: the customer has
stated it as a condition for proceeding past the initial depot and for expanding to 2
additional depots in 2027 (see sales_pipeline.csv OPP-2058, value £210,000).
Recommended Next Step
Engineering and Product to confirm whether REQ-03 (export) can be scheduled for Q4 2026;
currently listed only as a "candidate for Q4 quick-win sprint" in product_roadmap_q3.md,
not formally committed. Data retention gap (3 years vs current 18 months) should be raised
separately with Engineering and Finance (storage cost implication not yet estimated).

## 10_npi_readiness
NPI Readiness — NorthGuard Edge Gateway v2 (EG-200)
**Owner:** Tom Okafor, Engineering Lead / Felix Grant, Supply Chain Manager
**Target production start:** 2026-12-01 (supports Q1 2027 customer rollouts)
**Status as of:** 2026-10-01
Readiness Checklist
¦ Area ¦ Item ¦ Status ¦ Notes ¦
¦---¦---¦---¦---¦
¦ Design ¦ Hardware design freeze ¦ Closed ¦ Frozen 2026-08-15 ¦
¦ Design ¦ Firmware v2.0 feature-complete ¦ Closed ¦ 2026-09-05 ¦
¦ Validation ¦ Environmental / vibration testing (DV) ¦ Closed ¦ Passed, 2026-09-10 ¦
¦ Validation ¦ Field pilot (production validation, PV) ¦ **Open** ¦ Pilot planned with Kestrel Energy Systems site, not yet started — awaiting EG-200 pre-production units ¦
¦ Supply chain ¦ Main board supplier qualified (Helion Electronics GmbH) ¦ Open — at risk ¦ See supplier_status.csv HEL-006; same supplier currently has an active high-risk delay on EG-100 (HEL-004) ¦
¦ Supply chain ¦ Secondary/backup board supplier identified ¦ **Open — not started** ¦ No backup supplier evaluated; single-source risk given HEL-004 history ¦
¦ Supply chain ¦ Enclosure and cabling suppliers confirmed ¦ Closed ¦ Baltic Components SA (enclosure), Nordic Cabling AB (cabling) ¦
¦ Compliance ¦ CE marking documentation ¦ Open ¦ In progress, Engineering estimate completion 2026-11-10 ¦
¦ Compliance ¦ Data security review (edge firmware) ¦ Closed ¦ Completed 2026-09-20, no critical findings ¦
¦ Commercial ¦ Pricing model confirmed ¦ **Open** ¦ Pending alongside Energy Optimization add-on pricing (see commercial_quote_001.md, market_research_europe.md) ¦
¦ Commercial ¦ Install/training materials updated for EG-200 ¦ Not started ¦ Dependent on firmware and pricing finalisation ¦
Gating Issues for 2026-12-01 Target
1. **Field pilot (PV) not started.** Without pre-production units, the pilot cannot begin;
current EG-100 production is prioritised over EG-200 pre-production runs at Helion
Electronics GmbH, per Felix Grant's 2026-09-28 update. This is the primary schedule risk.
2. **Single-source supply risk.** No backup board supplier identified; given Helion's
current HEL-004 delay on the existing product, proceeding to GA on EG-200 without a
second source carries meaningful continuity risk.
3. **Pricing not finalised**, which blocks commercial readiness even if engineering and
supply chain items close on time.
Recommendation
Do not commit a firm EG-200 customer-facing launch date until (a) the field pilot has
started and (b) a backup supplier evaluation is at least scoped. Current 2026-12-01 target
should be treated as at risk, not committed, in any customer or pipeline communication
(relevant to sales_pipeline.csv opportunities referencing future hardware, e.g. OPP-2063).

## 11_weekly_operations_review
Weekly Operations Review — Week of 2026-10-05 to 2026-10-11
**Chaired by:** Ji Xiong, Head of Operations & Customer Programmes
**Attendees:** Elena Marsh (Product), Tom Okafor (Engineering), Priya Nandan (Customer Success),
Felix Grant (Supply Chain), Daniel Price (Finance)
Cost
• Gateway hardware cost pressure flagged: Helion Electronics GmbH delay (HEL-004) is now
running 7 weeks against a normal 4-week lead time, with knock-on cost exposure if Northstar
has to air-freight remaining units for Caldwell Precision Components to avoid a second SLA
breach (estimated additional cost £2,100, not yet approved by Finance).
• QUOTE-2026-041 (Harrow Industrial Holdings) discount of 8% still awaiting Finance Director
sign-off per standard threshold (>£50,000); Daniel Price to chase before end of week.
Quality
• False-positive alert rate post-Alerts 2.0: 11% (down from 18%, target 8%). Meridian Steel
Group (FB-014) still reporting 2-3 false alerts/week on Line 3; Tom Okafor to review whether
a Line 3-specific threshold tune is warranted versus waiting for a broader model update.
• INC-122 (Kestrel Energy Systems, missing energy data) still has no confirmed owner;
**action: Tom Okafor to assign an engineer and log in project_action_log.csv this week.**
Delivery
• INC-114 (Caldwell Precision Components) now 6 weeks past the contracted 4-week onboarding
SLA; customer relationship at risk ahead of OPP-2063 expansion decision. Felix Grant
reports no confirmed ship date from Helion as of this meeting.
• Fleet Rollup dashboard not started in Q3; now a stated condition in two live
negotiations (OPP-2019 Meridian Steel Group, OPP-2031 Harrow Industrial Holdings) worth
a combined £240,000. Elena Marsh to bring a revised engineering estimate to next week's
review.
Decisions Needed This Week
1. Approve or reject air-freight cost for Caldwell Precision Components gateway units
(Daniel Price / Felix Grant).
2. Assign owner for INC-122 investigation (Tom Okafor).
3. Confirm whether Fleet Rollup can be committed to a specific Q4 date for OPP-2019 /
OPP-2031 contract language (Elena Marsh, Tom Okafor, Sara Lindqvist).
Carried Over From Last Week (2026-09-28 to 2026-10-04)
• EG-200 backup supplier evaluation: **still not started.** Raised again this week by
Ji Xiong as a recurring open item (see npi_readiness.md); Felix Grant to propose a
shortlist by 2026-10-23.

## 12_decision_log
Decision Log — Northstar Systems (NorthGuard IIoT Platform)
DEC-009 ¦ 2026-07-19 ¦ Approved
**Decision:** Apply interim alert-threshold recalibration for Meridian Steel Group Line 3
gearbox, ahead of the broader Alerts 2.0 release.
**Owner:** Tom Okafor
**Rationale:** Three false-positive incidents in one month (INC-101) risked customer trust;
interim fix judged lower-risk than waiting 8 weeks for full Alerts 2.0 release.
DEC-011 ¦ 2026-09-18 ¦ Approved
**Decision:** Prioritise Fleet Rollup dashboard engineering over native mobile offline mode
for the Q4 2026 roadmap.
**Owner:** Elena Marsh, Tom Okafor
**Rationale:** Fleet Rollup is a stated condition in two live commercial negotiations worth
a combined £240,000 (OPP-2019, OPP-2031); mobile offline mode is linked to one smaller,
earlier-stage opportunity (OPP-2070, £27,000). Decision not yet reflected in a committed
delivery date — see ACT-218 (overdue) and weekly_operations_review.md.
DEC-014 ¦ 2026-09-12 ¦ Approved
**Decision:** Ship Predictive Maintenance Alerts 2.0 at 11% false-positive rate rather than
delay further to reach the original 8% target.
**Owner:** Tom Okafor, Elena Marsh
**Rationale:** 11% represented a substantial improvement (from 18%) and further delay was
judged to cost more in customer trust than the residual gap; customer feedback post-release
(FB-014) indicates the residual gap is still a live concern and may need revisiting.
DEC-017 ¦ 2026-09-05 ¦ Approved
**Decision:** Escalate Helion Electronics GmbH gateway delay to supplier account management
level rather than seeking an alternative supplier for the current EG-100 shortfall.
**Owner:** Felix Grant
**Rationale:** Switching supplier mid-order judged higher-risk and slower than escalating
within the existing relationship, given no qualified second source exists yet. **Status:**
outcome of escalation still pending as of 2026-10-11 (see weekly_operations_review.md);
this decision should be revisited if no committed ship date is received by 2026-10-18.
DEC-020 ¦ 2026-10-04 ¦ Pending
**Decision (proposed):** Approve air-freight of remaining EG-100 gateway units for Caldwell
Precision Components to avoid a second SLA breach (estimated cost £2,100).
**Owner:** Daniel Price (Finance), Felix Grant (Supply Chain)
**Status:** Not yet approved; raised in weekly_operations_review.md (week of 2026-10-05),
awaiting Finance sign-off.
DEC-022 ¦ 2026-10-11 ¦ Pending
**Decision (proposed):** Commit a specific Q4 2026 delivery date for Fleet Rollup dashboard
in contract language for OPP-2019 and OPP-2031.
**Owner:** Elena Marsh, Tom Okafor, Sara Lindqvist
**Status:** Not yet decided; dependent on a revised engineering estimate (ACT-218, overdue)
expected at the next weekly operations review.